## Summary
BSA v3 — Application Audit
GRID Property Ventures · Business Site Analysis · audited 25 Sep 2026 (after the AI removal and brand update)
Findings by area and severity
Area | High | Medium | Low | Total | Done
Stability & bugs | 4 | 2 | 0 | 6 | 4
Data & scoring | 3 | 7 | 3 | 13 | 1
Performance | 1 | 2 | 1 | 4 | 0
Security | 1 | 6 | 1 | 8 | 0
UX & accessibility | 2 | 8 | 0 | 10 | 2
Code health | 0 | 3 | 3 | 6 | 0
Operations | 3 | 2 | 0 | 5 | 3
Total | 14 | 30 | 8 | 52 | 10
Do these first (highest impact, mostly small effort)
1. F-01 / F-02 — remove the remaining transaction-prone queries (same crash as the old AI report)
2. F-03 — delete the leftover calls to the removed AI endpoint (404s and a fake 'writing' step)
3. F-07 — make the dashboard verdict and the Final Report recommendation always agree
4. F-49 / F-50 — auto-apply migrations on deploy and show the running build id
5. F-48 — CI on every push
6. F-32 / F-33 — mobile navigation and an accurate onboarding tour
7. F-04 — keep each pipeline slice inside the time limit
8. F-31 — rotate the exposed Google key and passwords
9. F-19 — run the Cavite/Batangas data loads, then re-test
10. F-42 / F-52 — remove leftover AI code and update the docs for handoff
How to use this workbook
• Audit Findings — every issue with the Problem, its Cause, How to implement the fix and the Desired result, plus evidence (file:line), effort and owner.
• Update the Status column (Open / In progress / Done / Won't do) as work lands — the Done counts above update automatically.
• Severity: High = can break the app, give a wrong recommendation, or expose data. Medium = a real quality or security gap. Low = hygiene.
• Priority is a formula from Severity (High → P1, Medium → P2, Low → P3). Effort: S ≈ under a day, M ≈ 1–3 days, L ≈ a week or more.
• Source shows whether an item is new from this audit or carried over from the 23 Sep backlog (docs/BSA_Improvement_Backlog.xlsx).
• Retired Items — earlier backlog items that no longer apply (AI removed) or are already done.
• Evidence was confirmed in the code on 25 Sep 2026; line numbers can drift as files change.

## Audit Findings
Audit Findings
Edit the Status column (drop-down) as work progresses. Priority is calculated from Severity.
ID | Area | Severity | Priority | Problem | Cause | How to implement | Desired result | Evidence (file:line) | Effort | Owner | Source | Status
F-01 | Stability & bugs | High | P1 | The analysis pipeline can crash with "Transactions are not supported in HTTP mode" — the same error that broke the AI report. | lib/modules/orchestrator.ts loads the run with findUniqueOrThrow + include (sites, franchisor, intake). Under the Neon HTTP adapter Prisma runs that as an implicit transaction, which HTTP mode rejects. | Replace with findUnique (flat select) + explicit null check, then read sites / franchisor / intake with separate flat queries. Add a lint rule or test that bans findUniqueOrThrow/findFirstOrThrow combined with include on request paths. | Running or re-running an intake never fails on the database adapter; one consistent data-access pattern across the app. | lib/modules/orchestrator.ts:80 | S | Dev team | New audit | Done
F-02 | Stability & bugs | High | P1 | The run report, full report and scorecard builders use the same transaction-prone query. | lib/modules/reportComposer.ts uses findUniqueOrThrow with include: { franchisor } on POST /api/reports, /api/reports/full and buildScorecards. | Same fix as F-01: flat findUnique + separate franchisor read + null check. | Run Report and PDF exports generate reliably on Netlify + Neon. | lib/modules/reportComposer.ts:206 | S | Dev team | New audit | Done
F-03 | Stability & bugs | High | P1 | "Re-run analysis" and New Intake submit still call the deleted AI endpoint, fire a 404 per site and show a fake "Writing analyses…" step. | When the AI report was removed, the client loops that POST /api/analysis-report after each run were left in place; errors are swallowed by .catch(() => null). | Delete the analysis-report loops and the "writing" phase in RunPipelineButton and SteppedIntakeWizard; update the button tooltip copy. | Re-run and submit finish as soon as the modules finish; no wasted requests or misleading status text. | components/RunPipelineButton.tsx:33-56; components/SteppedIntakeWizard.tsx:370 | S | Dev team | New audit | Done
F-04 | Stability & bugs | High | P1 | One pipeline slice can outlive the serverless time limit, and a killed site is retried forever. | The time budget is only checked between sites; each site can spend up to ~4.5 s warming the POI cache twice (orchestrator + Territory Guard) plus White-Space. The run route sets no maxDuration. analyzedAt is never written when the function is killed. | Set export const maxDuration on /api/runs/[id]/run; warm the POI cache once per site and pass the result to Territory Guard; add an attempt counter on candidate_site and mark the site failed after N attempts. | Every slice returns inside the platform limit; stuck sites fail clearly instead of looping. | lib/modules/orchestrator.ts:131,150; lib/modules/territoryGuard.ts:330; lib/places/poiCache.ts:125; app/api/runs/[id]/run/route.ts | M | Dev team | New audit | Done
F-05 | Stability & bugs | Medium | P2 | Two browser tabs (or a double click) can process the same pending sites at the same time. | The orchestrator picks pending sites with a plain read; nothing claims them before processing. | Claim each site with a conditional updateMany (e.g. set processing_started_at where analyzed_at is null and not recently claimed) and skip sites whose claim fails. | Each site is analysed exactly once per run; no duplicated work or racing writes. | lib/modules/orchestrator.ts:117-128 | M | Dev team | New audit | Open
F-06 | Stability & bugs | Medium | P2 | A rejected or failed intake leaves orphan brands and half-written runs. | For independent businesses the franchisor row is created before the 80% completeness check; intake, outlets, run and sites are then written one by one with no cleanup (no transactions on Neon HTTP). | Run all validation and the completeness gate before any write; wrap the write sequence in try/catch with compensating deletes (or use a pooled client for this route). | A failed submit leaves the database unchanged; no stray brands in Franchise Screening. | app/api/intake/route.ts:52,86,219 | M | Dev team | New audit | Open
F-07 | Data & scoring | High | P1 | The Site Dashboard verdict and the Final Report recommendation can disagree for the same site. | The dashboard uses the weighted composite score (scorecard.ts: Go ≥65, Caution ≥45, Site Fit 30%, capped when Site Fit is missing). The Final Report/PDF use summariseSite, which reads only Territory, Lease and Daypart with different Daypart cut-offs (60/40). | Make one source of truth: feed the composite band into summariseSite so the recommendation can never be better than the scorecard band (or add Site Fit to summariseSite with the same weights). Add a unit test asserting the two always agree. | A broker sees the same Proceed / Caution / No-Go call on the dashboard, the Final Report and the PDF. | lib/modules/scorecard.ts:40-42,102; lib/modules/siteVerdict.ts:87-144 | M | Dev team | New audit | Done
F-08 | Data & scoring | High | P1 | Provincial lease reads use an NCR-only rent-to-land calibration and NCR wording. | The ₱6–14 per ₱1,000 zonal band and the "typical NCR band" text were calibrated on NCR corridors but are applied to Davao, Cavite and Batangas zonal values. | Store a calibration band per region in the region registry; return 'unknown' and hide the cross-check when a region has none; make the note text region-aware. | Provincial rent-to-land cross-checks are either calibrated for that region or honestly withheld. | lib/modules/leaseMath.ts:272-331; lib/modules/leaseBenchmark.ts:180-182 | M | Dev team | New audit | Open
F-09 | Data & scoring | Medium | P2 | Several code paths still silently default to NCR. | Lease falls back to the Quezon City corridor for any region; zonal lookups default to 'NCR'; ingest sweeps default to the NCR grid. | Resolve the fallback corridor per region from the registry; return null / 'no data' when a region has no zonal rows; require --region on ingest scripts. | A Cavite or Batangas site is never scored against Metro Manila data without a clear flag. | lib/modules/orchestrator.ts:55,176; lib/modules/p2p3Modules.ts:282; lib/modules/leaseBenchmark.ts:62; lib/geo/zonalRow.ts:39; lib/ingest/places.ts:231,324,403,461 | M | Dev team | New audit | Open
F-10 | Data & scoring | Medium | P2 | Some modules report a value when they actually have no data. | Daypart's last-resort nearest demographic cell has no distance cap (can borrow another region's cell); a silently failed OSM warm returns 0 competitors, so Informal scores a perfect 100; Healthcare uses cnt ?? 0. | Cap the nearest-cell fallback (e.g. 5 km); propagate a 'coverage unknown' flag from the POI cache and return null scores when coverage failed; treat missing counts as null, not 0. | Missing data shows as "—" / low confidence, never as a strong score (Truth Layer rule). | lib/modules/p2p3Modules.ts:66-70,142,173; lib/places/poiCache.ts:129,186 | M | Dev team | New audit | Open
F-11 | Data & scoring | Medium | P2 | White-Space can recommend barangays in another region (e.g. Davao areas for an NCR site). | The White-Space ranking has no region or distance limit. | Filter candidate areas by the site's region and a maximum distance (e.g. ST_DWithin 10–15 km). | White-Space suggestions are always local and actionable for the broker. | lib/modules/p2p3Math.ts:387-389 | S | Dev team | New audit | Open
F-12 | Data & scoring | Medium | P2 | The schema allows duplicate or colliding reference data. | mall_property has no unique key but is upserted by mall name (same-name malls in different regions overwrite each other); lease_comp has no natural key; demographic_cell has no region column. | Add region to mall_property + unique (region, mall_name); add a natural key to lease_comp; add region to demographic_cell (backfill from admin_boundary); update the loaders. | Loading one province can never overwrite another's malls or comps; region-scoped reads become cheap. | prisma/schema.prisma:398-457; lib/ingest/loaders.ts:185 | M | Dev team | New audit | Open
F-13 | Data & scoring | Medium | P2 | A failed lease load can wipe a corridor's comps. | loadLease deletes each (format, corridor) group and re-inserts it without a transaction. | Insert the new rows first, then delete the old rows by id (or load through a pooled client inside a transaction). | Re-loading comps is always safe; a corridor is never left empty. | lib/ingest/loaders.ts:112-133 | S | Dev team | New audit | Open
F-14 | Data & scoring | Medium | P2 | Lease comps have no freshness rule. | observedDate is only used for ordering; old comps are never flagged or aged out. | Flag comps older than 18 months, down-weight or exclude them past 36 months, and show 'data as of' on the Lease tab. Optional broker endpoint to submit confirmed rents. | Rent benchmarks reflect the current market and say how recent they are. | lib/modules/leaseBenchmark.ts:122-153 | M | Dev team | Prior backlog D-03 | Open
F-15 | Data & scoring | Medium | P2 | The Site Fit 'accessibility' pillar is always empty. | No transport layer is loaded, so the 15% accessibility pillar is null for every site. | Load OSM transport features (jeepney/bus stops, rail stations, major roads) per region and score distance/density to them. | Site Fit reflects how easy a site is to reach — important for Filipino commuter traffic. | lib/modules/siteFit.ts | M | Dev team | Prior backlog D-01 | Open
F-16 | Data & scoring | Low | P3 | Trade areas are fixed circles. | Catchments are circles by format (600–1,200 m); rivers, highways and gated areas are ignored. | Use travel-time isochrones (self-hosted OSRM/Valhalla or an isochrone API), cached per site. | Catchments match how customers actually reach the site. | lib/modules/territoryMath.ts | L | Dev team | Prior backlog D-02 | Open
F-17 | Data & scoring | Low | P3 | Known NCR zonal gaps (San Juan missing, Valenzuela barangay grain). | The BIR workbooks for those RDOs were never loaded. | Download the current schedules and load them with npm run db:load-zonal. | The zonal cross-check works for every NCR city. | prisma/data/zonal/ | S | Owner | Prior backlog D-04 | Open
F-18 | Data & scoring | Low | P3 | Google-sourced POIs are recorded as 'manual'; age profiles are modelled from income; old runs keep pre-fix scores. | PoiSource enum has no 'google'; age_profile is a Projected model; historical runs were never re-run after the fix batches. | Add 'google' to PoiSource plus a provenance column; load PSA age-sex tables; run a one-off re-run script for historical runs. | Clean provenance, real age data, and consistent scores across all runs. | prisma/schema.prisma; prisma/enrichAgeProfiles.ts | M | Dev team | Prior backlog D-05/06/07 | Open
F-19 | Data & scoring | High | P1 | Cavite and Batangas are wired in code but have no reference data loaded yet. | The R-series built the loaders; the owner data loads (boundaries, OSM sweep, PSA population, BIR zonal, lease comps, malls, traffic AADT) have not been run. | Follow the one-province load order in docs/qa-history/QA_JOURNEY_FINDINGS_CALABARZON.md (boundaries → OSM ingest in a quiet window → demographics → zonal → lease → malls → traffic), then re-run a Cavite and a Batangas intake. | Provincial sites get real scores instead of 'no data' / Projected fallbacks. | docs/qa-history/QA_JOURNEY_FINDINGS_CALABARZON.md; prisma/data/*/README.md | L | Owner | R-series follow-up | Open
F-20 | Performance | High | P1 | White-Space loads every competitor POI and every demographic cell for each site. | No region/bbox filter on the reads; scoring is an in-memory areas × POIs loop in JavaScript. | Push the counting into PostGIS (ST_DWithin + GROUP BY area) scoped to the site's region/radius; compute once per run and cache by (run, concept). | White-Space runs in well under a second and keeps scaling as provinces are added. | lib/modules/p2p3Modules.ts:381-497 | M | Dev team | New audit / Prior A-02 | Open
F-21 | Performance | Medium | P2 | Missing and inefficient database indexes. | No index on module_result.pipeline_run_id (filtered on every dashboard load and cascade delete); nearest-row lookups ORDER BY ST_Distance (full scan) instead of the KNN <-> operator; duplicate GiST index on demographic_cell.geom; migration_lock.toml missing. | Add @@index([pipelineRunId]) to ModuleResult; rewrite nearest lookups with ORDER BY geom <-> point; drop the duplicate GiST index; commit migration_lock.toml. | Faster dashboards and module reads; a clean migration history. | prisma/schema.prisma:518-534; lib/modules/p2p3Modules.ts:69,189; prisma/migrations/ | S | Dev team | New audit | Open
F-22 | Performance | Medium | P2 | Reference-data loaders write one row at a time over Neon HTTP. | Loaders do find-then-write per row (2–3 round trips each), so a province-scale load is very slow. | Batch INSERT … ON CONFLICT in chunks of about 500 using a script-only client on the direct (pooled) connection. | Province loads finish in minutes, not hours. | lib/ingest/loaders.ts:55-63,185-192,216-230 | M | Dev team | Prior backlog A-03 | Open
F-23 | Performance | Low | P3 | /api/brands runs a full ILIKE scan of the POI table per catalog brand on every call. | No caching; the per-brand scans run one after another. | Precompute branch counts (materialised view or nightly job) or cache the response. | Franchise Screening loads instantly. | app/api/brands/route.ts:21-23 | S | Dev team | New audit | Open
F-24 | Security | Medium | P2 | The intake route can leak raw database error text to the browser. | The 500 response includes err.message; Prisma/Neon messages can contain query and column details. | Log the full error server-side; return a generic message plus a short reason code. | No internal details reach the client (passes a basic pen-test check). | app/api/intake/route.ts:219-220 | S | Dev team | New audit | Open
F-25 | Security | Medium | P2 | Nothing limits calls to paid Google APIs. | Any signed-in user (and registration is open) can call /api/places, /api/geocode and /api/maptiles; lat/lon/types/address inputs have loose bounds. | Add per-user daily quotas (reuse the DB rate limiter), tighten Zod bounds (PH bounding box, max lengths), and consider invite-only registration. | Predictable Google API cost; no abuse through the proxy routes. | app/api/places/route.ts:11-25; app/api/geocode/route.ts:7-13; app/api/maptiles/route.ts:12 | M | Dev team | New audit | Open
F-26 | Security | Medium | P2 | Sessions can't be revoked, and role changes don't take effect until the token expires. | Stateless 8-hour JWTs; logout only clears the cookie; role and franchisor are read from the token, not the database. | Add token_version (or sessions_valid_after) to app_user; bump it on logout-all, password change and role change; check it in getSession. | Logging out, changing a password or demoting a user takes effect immediately. | lib/auth/auth.ts:42-64; app/api/auth/logout/route.ts:6; app/api/auth/password/route.ts:43 | M | Dev team | New audit / Prior S-03 | Open
F-27 | Security | Medium | P2 | The login page ships prefilled with demo credentials on production. | Default email/password state and a demo hint are hard-coded in the login page, even though demo logins are refused on deployments. | Render the defaults and the hint only when mock auth is enabled (pass a server flag to the page). | Production users see a clean login with no dead or sensitive-looking credentials. | app/(auth)/login/page.tsx:12-13,76 | S | Dev team | New audit | Open
F-28 | Security | Medium | P2 | The password-change route has no rate limit. | A hijacked session could brute-force the current password. | Apply the existing checkLimit to /api/auth/password. | Password change is protected like login. | app/api/auth/password/route.ts:36 | S | Dev team | New audit | Open
F-29 | Security | Low | P3 | Several small hardening gaps. | Territory Guard has no isUuid guard (malformed ids return 500); authenticated map tiles are sent Cache-Control: public; the login IP limiter trusts x-forwarded-for off Netlify and fails open on DB errors; the user's email is written into brand 'positioning' text. | Add the isUuid guard; switch tiles to private caching; trust only the platform client-IP header and fail closed; stop writing the email into brand text. | Clean results on the low-severity pen-test checks. | app/api/territory-guard/route.ts:33; app/api/maptiles/[z]/[x]/[y]/route.ts:36; lib/auth/rateLimit.ts:37-52; app/api/franchisors/route.ts:103 | S | Dev team | New audit | Open
F-30 | Security | Medium | P2 | The CSP still allows inline scripts and there is no central route guard. | Next 14 bootstrap needs 'unsafe-inline' without nonces; there is no middleware.ts, so every new route must remember its own auth check. | Add middleware.ts that generates a per-request nonce for a strict CSP and redirects unauthenticated requests for app pages and APIs. | Stronger XSS protection, and auth that can't be forgotten on a new route. | next.config.mjs:36 | M | Dev team | Prior backlog S-02/S-04 | Open
F-31 | Security | High | P1 | Exposed credentials still need rotating. | A Google API key was exposed in keys.docx and real account passwords were in an old database dump (repo history since cleaned). | Rotate the Google key (restrict by API + referrer) and reset the affected passwords; confirm the repo is private. | No credential that was ever exposed remains valid. | Owner action (Google Cloud console, Netlify env) | S | Owner | Prior backlog S-01 | Open
F-32 | UX & accessibility | High | P1 | There is no navigation on phones. | Below the md breakpoint the sidebar is hidden; the mobile top bar only has the logo and Logout. | Add a hamburger drawer (or bottom tab bar) that renders the same SidebarNav items plus Settings. | Brokers in the field can reach Franchise Screening, New Intake and Settings from a phone. | app/(app)/layout.tsx:34,59-64 | S | Dev team | New audit / Prior U-01 | Done
F-33 | UX & accessibility | High | P1 | The first-run tour points at menu items that no longer exist. | Tour steps still target nav-modules and nav-reports and describe removed screens; anchored steps also miss on mobile. | Rewrite the tour for the current menu (Franchise Screening → New Intake → Site Dashboard → Final Report/PDF); skip or re-anchor steps on mobile. | New users get an accurate guided tour. | components/OnboardingTour.tsx:30-58,91-92 | S | Dev team | New audit | Done
F-34 | UX & accessibility | Medium | P2 | Removed pages are still linked or reachable. | /reports is linked from the dashboard; /explore, /modules and /scorecard still build and load by URL (Scorecard badges also fail contrast: white text on green/amber). | Decide per page: remove the page and its components (ModulesView, PlacesExplorer, ReportView, PrintButton) with redirects, or keep and fix it. Update the RunDashboard links. | No dead-end or off-brand screens, and a smaller codebase for handoff. | components/RunDashboard.tsx:69; app/(app)/{explore,modules,scorecard,reports}/page.tsx; app/(app)/scorecard/page.tsx:19-20 | S | Dev team | New audit | Open
F-35 | UX & accessibility | Medium | P2 | Keyboard and screen-reader users can't use the site tabs properly, and focus is invisible. | Tabs are plain buttons with no tab roles, aria-selected or arrow keys; there are no focus-visible styles anywhere and .field removes the outline. | Add role=tablist/tab/tabpanel, aria-selected and arrow-key handling; add focus-visible:ring-2 ring-accent to buttons, nav items and fields. | WCAG 2.2 AA keyboard and focus compliance. | components/SiteIntelligenceTabs.tsx:204-217; app/globals.css:52-61 | S | Dev team | New audit | Open
F-36 | UX & accessibility | Medium | P2 | Some inputs and icon buttons have no accessible label. | Intake outlet/candidate rows rely on placeholders; the location picker search and its ✕ close button have no labels. | Add visible labels or aria-labels to every input and icon button. | Forms work with screen readers and are clearer for older users. | components/SteppedIntakeWizard.tsx:675-702; components/LocationPicker.tsx:131-134 | S | Dev team | New audit | Open
F-37 | UX & accessibility | Medium | P2 | Layouts overflow on small screens. | Intake rows use a fixed grid-cols-12; the lease comps table is overflow-hidden. | Use grid-cols-1 sm:grid-cols-12 for the rows; switch the table wrapper to overflow-x-auto. | The intake and the Lease tab work on phones and small laptops. | components/SteppedIntakeWizard.tsx:674,699; components/SiteIntelligenceTabs.tsx:510 | S | Dev team | New audit | Open
F-38 | UX & accessibility | Medium | P2 | There are no branded loading, error or not-found screens. | No loading.tsx / error.tsx / not-found.tsx files exist, so failures show the default Next.js page. | Add them under app/(app)/ in the GRID theme, with a retry action and plain-language copy. | Errors are calm, branded and recoverable. | app/(app)/ | S | Dev team | New audit | Open
F-39 | UX & accessibility | Medium | P2 | Very small text is used widely (9–11px). | 63 uses of text-[9–11px], often in muted grey — hard to read for older users. | Set a 12px minimum (13–14px for body copy); raise muted-text contrast where it sits on hover surfaces. | Readable for the older / tech-resistant audience named in the brand guidelines. | components/SiteIntelligenceTabs.tsx; components/SteppedIntakeWizard.tsx:601 | M | Dev team | New audit | Open
F-40 | UX & accessibility | Medium | P2 | The proxy lease corridor can't be corrected, and the map ring colour can lag the verdict. | When no corridor matches, the Lease tab says it's a proxy but offers no picker; TerritoryMap computes its own verdict. | Add a corridor picker (corridorsForRegion + corridors that have comps) that re-benchmarks; pass the blended verdict into TerritoryMap. | Brokers can fix the corridor in one click, and the map always matches the verdict. | components/SiteIntelligenceTabs.tsx; components/TerritoryMap.tsx | S | Dev team | Prior backlog U-02/U-03 | Open
F-41 | UX & accessibility | Medium | P2 | The UI redesign has not been done yet. | Branding (palette, fonts, logo) is applied, but hierarchy, spacing and components were never designed as a system. | Run docs/DESIGN_PROMPT.md in a Claude design session, then implement the resulting tokens and component recipes. | A cohesive, professional UI where the Proceed / Caution / No-Go call is obvious in under 5 seconds. | docs/DESIGN_PROMPT.md | L | Owner + Dev team | New audit | Open
F-42 | Code health | Medium | P2 | Leftover AI code, config and docs remain after the AI report was removed. | lib/ai/index.ts still lists 'vectorshift'; analysisCache/mockAnalysis/outputCheck/analysisPrompts are only used by tests; the orchestrator still deletes module='analysis' rows and site/page reads them; the PipelineUsage model remains; .env.example keeps a VectorShift section (with a real-looking pipeline id); generateGrounded writes placeholder aiGeneration rows; UI copy still says 'write-up'. | Remove the unused lib/ai files and their tests; drop the vectorshift provider option; remove the 'analysis' reads/deletes; drop PipelineUsage/AiGeneration via migration (or mark them reserved); clean .env.example and UI copy; remove VECTORSHIFT_* / ANALYSIS_BACKGROUND / INTERNAL_JOB_SECRET from Netlify. | A codebase that matches the product, with no dead AI paths for the dev team to puzzle over. | lib/ai/*; lib/modules/orchestrator.ts:8,113; app/(app)/site/page.tsx:66; prisma/schema.prisma:592-620; .env.example | M | Dev team | New audit | Open
F-43 | Code health | Medium | P2 | Critical server modules have no tests. | Tests cover pure math only: nothing tests orchestrator slicing/resume/failure, p2p3Modules (White-Space scope, fallbacks), territoryGuard, leaseBenchmark zonal resolution, siteFit, poiCache or the loaders; no test checks that summariseSite agrees with the scorecard; no end-to-end journey test. | Add integration tests against a Neon test branch (or local Postgres + PostGIS in CI); add the verdict-agreement test; add Playwright smoke tests (login → intake → run → site tabs → PDF). | Regressions are caught before deploy, and the handoff is backed by tests. | tests/unit; lib/modules/* | L | Dev team | New audit / Prior A-04 | Open
F-44 | Code health | Low | P3 | Very large components are hard to maintain. | SiteIntelligenceTabs.tsx (~1,100 lines), SteppedIntakeWizard.tsx (~750), FranchiseScreeningView.tsx (~600). | Split each tab and wizard step into its own file; move shared tone maps and chips to components/ui. | Smaller, reviewable files that the dev team can work on in parallel. | components/SiteIntelligenceTabs.tsx; components/SteppedIntakeWizard.tsx; components/FranchiseScreeningView.tsx | M | Dev team | New audit | Open
F-45 | Code health | Low | P3 | Helpers and colours are duplicated. | fmtPeso ×2, fmtPhp ×2, three different peso helpers (one prints 'PHP'), VERDICT_COLOR ×2; chart/map hex colours that don't match the tokens (#38a574 vs #3EAF7F). | Consolidate formatting in lib/util/format.ts; export one palette module (e.g. lib/ui/palette.ts) used by the Tailwind config, charts and maps. | One definition per helper and colour, and consistent money formatting. | components/SiteIntelligenceTabs.tsx:133; components/FranchiseScreeningView.tsx:76; lib/modules/siteVerdict.ts:56; components/LeaseDistributionChart.tsx:19-21; lib/geo/mapGeometry.ts:32 | S | Dev team | New audit | Open
F-46 | Code health | Low | P3 | Lint suppressions and small inconsistencies. | Nine eslint-disable react-hooks/exhaustive-deps and one 'as any'; font-mono used outside the brand tokens; Settings uses toLocaleDateString (server timezone); unused ModuleKind enum values. | Fix the hook dependencies properly; type the PDF element; use the brand font tokens; use the Manila date helper; drop or document the unused enum values. | A clean lint run and consistent behaviour. | components/{AnalysisSequence,GapsMap,LocationPicker,SteppedIntakeWizard,TerritoryMap}.tsx; app/(app)/settings/page.tsx:31; prisma/schema.prisma:114-129 | S | Dev team | New audit / Prior A-05 | Open
F-47 | Code health | Medium | P2 | Pages read the database directly instead of going through the API/service layer. | Several server pages query Prisma directly, which goes against the API-first rule for the handoff. | Create lib/services/{runs,sites,reports}.ts used by both API routes and pages (or have pages call the API). | One data path per resource that is easier to secure, test and hand over. | app/(app)/*/page.tsx | M | Dev team | Prior backlog A-01 | Open
F-48 | Operations | High | P1 | There is no CI pipeline. | Typecheck, tests and build only run when someone runs them by hand. | Add GitHub Actions on every push/PR: npm ci → prisma generate → typecheck → test → build. | Broken code can't reach main unnoticed. | .github/workflows/ci.yml (new) | S | Dev team | Prior backlog O-01 | Done
F-49 | Operations | High | P1 | Database migrations are applied by hand. | Several incidents came from forgetting prisma migrate deploy after a deploy. | Run prisma migrate deploy in the Netlify build (or fail the build when migrations are pending). | Code and database schema are always in sync after a deploy. | netlify.toml | S | Dev team | Prior backlog O-02 | Done
F-50 | Operations | High | P1 | Local and production share one database, and there's no way to tell which build is live. | A single Neon database serves every environment; recent fixes looked 'not working' because the deployed build was stale. | Use Neon branches for dev / preview / production with per-context Netlify env vars; show the build/commit id in the footer or on /settings. | Safe testing without touching live data, and an easy check of which build is running. | Neon console; Netlify env contexts | M | Dev team | Prior backlog O-03 + new audit | Done
F-51 | Operations | Medium | P2 | There is no error monitoring. | Server errors only appear in Netlify function logs, so issues are found by users. | Add Sentry (or similar) for server and client, with request ids and reason codes. | Problems are seen and diagnosed before users report them. | (new integration) | S | Dev team | Prior backlog O-04 | Open
F-52 | Operations | Medium | P2 | The documentation is out of date for the handoff. | README, HANDOFF, API_REFERENCE and DATA_DICTIONARY still describe the VectorShift analysis endpoint; the .env.example demo account doesn't match the code; the new Proceed/Caution/No-Go rules aren't documented. | Update the docs; add a 'How the recommendation is decided' section (siteVerdict rules + scorecard bands) and the regional data-load runbook. | The dev team can onboard from the docs alone. | README.md:22,60; docs/HANDOFF.md:42,63,100; docs/API_REFERENCE.md:165-169; docs/DATA_DICTIONARY.md:122; .env.example | S | Dev team | New audit | Open

## Retired Items
Retired or already-done items from the 23 Sep backlog
ID | Area | Item | Why retired / status
I-01 | AI layer | VectorShift prompt not updated for the new input | Retired — AI analysis removed (25 Sep 2026)
I-02 | AI layer | Live AI can exceed Netlify's time limit (background function) | Retired — AI analysis removed; background function deleted
I-03 | AI layer | Semantic search (pgvector) not used | Retired for now — no AI generation; revisit only if AI returns
I-04 | AI layer | No admin view of AI usage and cost | Retired — no paid AI calls remain
U-04 | User experience | Stale AI write-up after saving an asking rent | Retired — the Final Report is now computed live from module data
R-01 to R-08 | Regional expansion | Region registry, boundaries, tiled Overpass, demographics, zonal, lease corridors, malls/traffic, regional QA | Done in code (24 Sep 2026). Data loads carried forward as F-19
— | Stability | Analysis-report 502 'Transactions are not supported in HTTP mode' | Resolved by removing the AI report; the same query pattern is still in the pipeline → F-01 / F-02
— | UX | React hydration errors #418 / #423 | Resolved — deterministic number and Manila-time formatting