## Summary
BSA v3 — What still needs improvement (for approval)
Development prototype → clean, functioning handover to Grid's development team. Review the Backlog, set Approval per row, then we proceed in batches.
Backlog by area and priority
Area | P1 | P2 | P3 | Total | Approved
Regional expansion | 4 | 4 | 0 | 8 | 0
Data & scoring | 0 | 4 | 3 | 7 | 0
AI layer | 2 | 1 | 1 | 4 | 0
Architecture | 0 | 4 | 1 | 5 | 0
Operations | 3 | 1 | 0 | 4 | 0
Security | 1 | 2 | 1 | 4 | 0
User experience | 1 | 3 | 0 | 4 | 0
Total | 11 | 19 | 6 | 36 | 0
How to read the workbook
• Improvement Backlog — every open item: what needs improving, current state, how to improve, the implementation needed and the desired outcome. Yellow 'Approval' column is yours to fill (Approve / Defer / Reject / Discuss).
• Cavite-Batangas Data Plan — 12 steps to source Cavite and Batangas data (Overpass API + PSA, BIR, broker and DPWH sources) and load it into Neon with its Truth Layer.
• Overpass Query Templates — ready-to-test Overpass QL for provinces, tiles, brands, malls, transport and barangay boundaries.
• Data Coverage Matrix — what data exists today for NCR, Davao, Cavite and Batangas, and where the gaps get filled from.
• Sources — references used for the Overpass guidance, admin levels, census figures and BIR RDOs.
• Suggested first batch (P1): R-01, R-02, R-03, R-04, I-01, I-02, O-01, O-02, O-03, S-01, U-01.

## Improvement Backlog
BSA v3 — Improvement Backlog (development prototype → clean handover)
Status as of 23 Sep 2026, after fix batches 1–5. Set 'Approval' per row (Approve / Defer / Reject / Discuss). Priority: P1 = before handover · P2 = early dev-team sprint · P3 = later. Effort: S ≤1 day · M 2–5 days · L 1–3 weeks.
ID | Area | What still needs improvement | Current state / why it matters | How to improve | Implementation needed | Desired outcome | Priority | Effort | Owner (skill) | Depends on | Approval | Reviewer notes
R-01 | Regional expansion | Region support is hard-coded to NCR (and part of Davao) | ingestOsm.ts sweeps one fixed NCR_BBOX; the warm grid (NCR_CENTERS), corridor resolver (inferCorridor), zonal city matcher (canonicalNcrCity) and populate.ts regions are NCR/Davao only. A Cavite or Batangas site gets proxy lease comps (Quezon City; Bacoor → Las Piñas), no zonal cross-check, no mall or traffic context, and no demographics. | Introduce a single region registry and make every ingest script and resolver region-aware, so adding a province is configuration + data, not code changes. | New lib/geo/regions.ts: { key, name, psgcProvinceCodes, bbox, overpassArea, warmCentres, corridors }. Add --region=<key> to ingestOsm.ts, populate.ts and the zonal ETL. Replace canonicalNcrCity/inferCorridor with canonicalCity(region)/inferCorridor(region). Add region + province to candidate_site (derived from the pinned point). | Any supported province can be switched on by adding a registry entry and loading its data. Cavite and Batangas sites are analysed on local data instead of NCR proxies. | P1 | M | 02 Database · 01 Senior Web
R-02 | Regional expansion | No real administrative boundaries (barangay / city polygons) | demographic_cell.geom is a 600 m circle around a centroid, not the barangay shape. POIs are stored with city/barangay = NULL, so nothing can be filtered or reported by LGU. | Load official PSGC boundary polygons (region → province → city/municipality → barangay) and tag every POI and site with its PSGC codes by point-in-polygon. | New table admin_boundary (psgc_code PK, level, name, parent_psgc, geom MultiPolygon, GiST index, truth_layer Verified). Loader prisma/loadBoundaries.ts reading the PSGC shapefiles (altcoder/philippines-psgc-shapefiles, MIT, PSGC Q4-2023). SQL backfill: UPDATE poi SET city/barangay/psgc FROM admin_boundary WHERE ST_Contains. Same for candidate_site and mall_property. | Every point knows its barangay, city and province. Reports, White-Space areas and zonal lookups use true LGU boundaries. | P1 | M | 02 Database
R-03 | Regional expansion | OSM/Overpass sweep truncates results in dense areas | Each vertical is fetched with ONE bbox query for all of NCR and 'out center 600' (brands: 200). Dense categories (food, convenience, pharmacy) hit the cap, so coverage is silently incomplete. Scaling that to a whole province is worse. | Tile each region into ~0.05°–0.1° cells and query per tile + vertical, sequentially with pauses; if a tile returns the cap, split it into four and retry. | osmService.establishmentsInTiles(region, vertical): adaptive quad-tiling, 2.5 s pause, endpoint rotation (already present), resumable checkpoint (poi_coverage rows with source='bulk'). Log per-tile counts. Keep total ≤ ~10,000 queries/day per Overpass guidance. | Complete, non-truncated establishment coverage per province, reproducible and resumable. | P1 | M | 02 Database · 06 Research | R-01
R-04 | Regional expansion | Demographics exist only for NCR (283 barangays) + 13 Davao cells | Site Fit demand, Daypart and White-Space need population. Outside NCR, Site Fit can't score, so the composite is capped at CAUTION and confidence reads Low. | Load PSA 2020 Census barangay populations for Cavite and Batangas onto the real barangay polygons; keep estimated bands (income, daytime) clearly Assumed. | Source: PSA 2020 CPH barangay tables (Region IV-A). ETL → prisma/data/demographics.<region>.json (psgc_code, barangay, city, population [Verified], income_band/daytime_pop [Assumed]) → loadDemographics with geom from admin_boundary. OSM barangay nodes' population tag is a cross-check only. | Cavite (4,344,829 people, 2020) and Batangas (2,908,494) sites get real demand scores and White-Space areas, with honest Truth Layers. | P1 | M | 02 Database · 06 Research | R-02
R-05 | Regional expansion | BIR zonal values cover NCR only | Lease zonal cross-check and the Land zoning screen return 'unknown' outside NCR. | Run the existing NCR zonal ETL on the BIR schedules for the Cavite and Batangas RDOs and load with region = 'IV-A'. | Collect latest BIR zonal workbooks: RDO 54A (Trece Martires, East Cavite), RDO 54B (Bacoor, West Cavite), RDO 58 and 59 (Batangas). Reuse the NCR ETL (label canonicalisation, ₱ parsing, barangay + city grain). Extend canonicalCity for provincial LGUs. Load via loadZonal (idempotent natural key). | Zonal band, rent-to-zonal cross-check and zoning screen work for Cavite and Batangas — still framed as tax-reference floors only. | P2 | M | 02 Database · 07 Broker | R-01
R-06 | Regional expansion | No lease comparables outside NCR/Davao corridors | Lease Benchmark falls back to a Quezon City proxy (flagged Projected) for every Cavite/Batangas site. | Define provincial corridors and collect at least 5 comps per corridor × format from Grid's broker network and public listings. | Corridors (proposal): Bacoor/Molino, Imus, Dasmariñas, General Trias/Tanza, Tagaytay, Batangas City, Lipa, Sto. Tomas/Tanauan. Capture template (format, corridor, base rent ₱/sqm, CUSA, escalation, term, observed_date, source) → lease.<region>.json → loadLease. Truth: Verified only for signed/confirmed leases, else Assumed. | Real corridor benchmarks for the main provincial trade areas; proxy flag disappears for those sites. | P2 | L | 07 Broker · 02 Database | R-01
R-07 | Regional expansion | Mall and traffic context missing for provinces | mall_property has 33 NCR malls; traffic_corridor has 15 NCR/Davao corridors. Provincial sites get 'no mall nearby' and a POI-count traffic proxy. | Seed malls from OSM (shop=mall) with broker-reviewed tier/footfall; add major provincial arterials with DPWH AADT as traffic corridors. | Overpass shop=mall per province → review sheet (tier A/B/C, footfall band = Assumed) → malls.<region>.json → loadMalls. Traffic: DPWH AADT for e.g. Aguinaldo Hwy, Governor's Drive, Molino Blvd, SLEX/STAR Tollway, Batangas–Lipa roads → trafficSeasonality rows (Assumed). | Mall and Land/Traffic modules score provincial sites on real context. | P2 | M | 02 Database · 07 Broker | R-02
R-08 | Regional expansion | No regional QA pass | Davao and NCR had 'brutal' QA runs; provinces have none. | Run the scripted QA journey for 8–10 realistic Cavite/Batangas scenarios after data load. | Copy scripts/qa_davao_brutal.ts → qa_calabarzon.ts (Imus milk tea, Dasmariñas pharmacy, Lipa QSR, Batangas City laundry, Tagaytay café…). Check: no proxy flags, Truth mix, confidence not Low by default, zero console errors. Record in docs/qa-history. | Signed-off provincial journeys before brokers use Cavite/Batangas. | P2 | S | 08 Journey QA · 11 Code QA | R-01..R-07
D-01 | Data & scoring | Site Fit 'accessibility' pillar is always empty | The 15% accessibility pillar is null for every site (no transport layer), so Site Fit only uses demand + competition. | Score access from OSM transport features (jeepney/bus stops, rail stations, main roads) within walking distance. | Overpass: public_transport=platform¦stop_position, railway=station, highway=primary¦trunk within 500 m → poi category 'transport' (already in enum). siteFit.ts: access = f(stops within 400 m, station within 800 m, frontage on primary road). Unit tests. | Site Fit uses all three pillars; access-rich sites score higher. | P2 | M | 02 Database · 01 Senior Web | R-03
D-02 | Data & scoring | Trade areas are fixed circles | Catchments are circles by format (600–1,200 m). Rivers, highways and gated villages make real walk/drive areas very different. | Replace circles with travel-time isochrones for the candidate and nearby outlets. | Self-host OSRM/Valhalla or use an isochrone API server-side; cache polygons per site in a new column; overlap = ST_Area(ST_Intersection). Keep circles as fallback. | More realistic cannibalization and catchment population, especially in provinces. | P3 | L | 02 Database · 06 Research | R-02
D-03 | Data & scoring | Lease comp set is thin and ages silently | 80 comps across 15 corridors; most are Assumed; no freshness rule. | Add a comp feedback loop: brokers submit confirmed rents; age comps out after 24 months. | API POST /api/lease-comps (staff/broker, Zod, audit), observed_date required; benchmark filters to ≤24 months (configurable) and shows sample age. Admin review queue. | Growing, dated, broker-verified comp set; fewer low-sample reads. | P2 | M | 03 API · 02 Database · 07 Broker
D-04 | Data & scoring | Known zonal gaps in NCR | San Juan zonal values are missing entirely; Valenzuela barangay grain missing (the source folder held a Taguig duplicate). | Obtain the correct BIR workbooks and re-run the zonal ETL. | Download current RDO schedules for San Juan and Valenzuela → prisma/data/zonal.real.json → npm run db:populate:ncr. | Complete NCR zonal coverage. | P2 | S | 02 Database
D-05 | Data & scoring | Google-sourced POIs recorded as 'manual' | PoiSource enum has only osm ¦ manual, so provenance of Places-ingested rows is lost. | Add 'google' to PoiSource and a raw_tags/provenance JSON column. | Prisma enum migration (ALTER TYPE ADD VALUE), update lib/ingest/places.ts, backfill where possible. | Every POI's source is traceable (licensing + Truth Layer honesty). | P3 | S | 02 Database
D-06 | Data & scoring | Age profiles are modelled from income | demographic_cell.age_profile is a Projected model from income band (used by Healthcare). | Replace with PSA age-sex distribution by city/municipality. | PSA 2020 CPH age tables → enrichAgeProfiles.ts reads real distribution; Truth Verified at city grain, Assumed when down-scaled to barangay. | Healthcare catchment uses real age data. | P3 | M | 02 Database | R-04
D-07 | Data & scoring | Old runs keep pre-fix scores | Runs created before 23 Sep 2026 still show old confidence/labels until re-run; the dashboard keeps a legacy confidence fallback for them. | Bulk re-run historical runs once migrations are applied, then remove the legacy fallback. | Admin script scripts/rerunAll.ts (loops runPipeline(id,{refresh:true}) with pauses); then delete the fallback branch in lib/modules/dashboard.ts. | All runs scored by one rule set; less legacy code for the dev team. | P2 | S | 01 Senior Web
I-01 | AI layer | VectorShift prompt not yet updated for the new input | The app now sends the site schema + interpretation reference; the prompt inside VectorShift still says 'use ONLY the schema'. | Add one line to the VectorShift prompt and version the prompt text in the repo. | Prompt line: 'An INTERPRETATION REFERENCE may follow the schema — use it only to understand the fields; cite figures only from the schema.' Copy the live System + Prompt into lib/ai/prompts/vectorshift.v4.md with a version id logged on each generation. | Prompt changes are reviewable in git; write-ups stay grounded. | P1 | S | 10 AI Systems
I-02 | AI layer | Live AI can exceed Netlify's function time limit | Each site's write-up must finish inside one synchronous function (≤26 s). Slow model responses surface as 502 'function_timeout'. | Move generation to a Netlify Background Function (runs up to 15 min) and let the UI poll the existing status endpoint. | netlify/functions/analysis-background.ts calls generateAnalysisReport; POST /api/analysis-report enqueues and returns 202; the Analysis tab already polls GET /api/analysis-report. Keep the per-site lock. | No AI timeouts regardless of model latency. | P1 | M | 10 AI Systems · 03 API
I-03 | AI layer | Semantic search (pgvector) is not used | doc_chunk.embedding + HNSW index exist but retrieval is keyword-only; fine for 20 chunks, weak as the corpus grows. | Add an embedding provider and hybrid (keyword + vector) retrieval. | EMBEDDING_PROVIDER env; embed chunks at seed time; retrieve() = tsvector rank ⊕ cosine (<=>) with RRF merge; tests with a fixed corpus. | Better grounding for the AI as methodology/market docs grow. | P3 | M | 10 AI Systems · 02 Database
I-04 | AI layer | No admin view of AI usage and cost | pipeline_usage records cost, latency and failures but nothing displays it. | Add an admin-only usage page. | GET /api/admin/usage (isAdmin) aggregating by day/user/brand; /settings/usage page with totals, failure rate, p95 latency. | Grid can monitor AI spend and reliability. | P2 | S | 03 API · 01 Senior Web
A-01 | Architecture | Pages read the database directly (not API-first) | 7 server pages (intake, modules, reports, runs, scorecard, settings, site) plus the app layout query Prisma directly. Access checks are applied and nothing leaks, but it deviates from the API-first rule. | Move page data loading behind lib/ services shared with the API routes (or call the routes). | Create lib/services/{runs,sites,reports}.ts used by both routes and pages; pages stop importing prisma. | One data-access path; easier production hardening and caching. | P2 | M | 03 API · 01 Senior Web
A-02 | Architecture | White-Space is O(areas × POIs) per site | Every site loads all competitor POIs and all demographic cells and scores in JavaScript. Provinces will multiply the cost. | Push tiering/counting into PostGIS and compute once per run. | SQL with ST_DWithin + GROUP BY area; cache result per (run, concept); restrict to the site's region. | White-Space stays fast as data grows. | P2 | M | 02 Database | R-01
A-03 | Architecture | Reference-data loaders are row-by-row | Loaders do find-then-write per row over Neon HTTP; a province-scale load will be slow and partial loads aren't atomic. | Batch upserts (INSERT … ON CONFLICT) in chunks of 500 using the pooled/direct connection for scripts. | Script-only PrismaClient on DIRECT_URL (not the HTTP adapter); $executeRaw batch upserts; per-dataset transaction. | Province loads in minutes, all-or-nothing. | P2 | M | 02 Database
A-04 | Architecture | No automated end-to-end journey tests | Unit tests (331) cover logic; the journey is only checked manually. Playwright is already a dev dependency. | Add Playwright smoke tests for the core journey against a seeded preview database. | tests/e2e: login → intake (demo prefill) → run → site tabs → Analysis (stub AI) → run report. Run in CI on a Neon branch. | Regressions like the hydration error are caught before deploy. | P2 | M | 11 Code QA · 08 Journey QA | O-01
A-05 | Architecture | Unused schema values | ModuleKind values financial, risk, calibration are never written. | Remove or document as reserved. | Either a migration dropping them (Postgres enum rebuild) or a comment in schema.prisma + data dictionary. | A schema the dev team can trust. | P3 | S | 02 Database
O-01 | Operations | No CI pipeline | Typecheck, tests and build only run when someone runs them. | GitHub Actions on every push/PR. | .github/workflows/ci.yml: npm ci → prisma generate → npm run typecheck → npm test → npm run build; npm audit (fail on high). | Broken code can't reach main unnoticed. | P1 | S | 11 Code QA
O-02 | Operations | Migrations are applied by hand | Every batch needed a manual 'prisma migrate deploy'; forgetting it caused the analysis 502s. | Apply migrations automatically on deploy (or block the deploy if pending). | Netlify build: npx prisma migrate deploy && npx prisma generate && npm run build (DIRECT_URL set in Netlify), or a CI step before deploy. | Code and database can't drift apart. | P1 | S | 02 Database · 12 Delivery
O-03 | Operations | Single environment | Local and production point at the same Neon database. | Separate dev / preview / production using Neon branches and Netlify deploy contexts. | Neon branch per environment; Netlify env vars per context; preview deploys use a preview branch. | Testing never touches production data. | P1 | S | 12 Delivery · 04 Security
O-04 | Operations | No error monitoring | Server errors only appear in Netlify function logs. | Add error tracking and structured logs. | Sentry (or similar) for Next.js server + client; log request id + reason codes already produced by the API. | Problems are seen and triaged before users report them. | P2 | S | 12 Delivery
S-01 | Security | Rotate exposed credentials | The Google API key in keys.docx is exposed; real account passwords were in the old public database dump. | Rotate the key (restrict by API + referrer) and reset affected passwords. | Google Cloud console → new key → GOOGLE_API_KEY in Netlify; revoke old. Force password reset for accounts that existed before 23 Sep. | No known-compromised credentials remain. | P1 | S | 04 Security
S-02 | Security | CSP still allows inline scripts | Next 14 needs 'unsafe-inline' for its bootstrap scripts. | Nonce-based CSP via middleware. | middleware.ts generates a nonce per request, sets CSP header, passes nonce to next/script. | Stronger XSS protection. | P2 | M | 04 Security
S-03 | Security | Sessions can't be revoked | JWTs are valid for 8 h even after logout or a password change. | Add a token version to app_user and check it on each request. | app_user.token_version; increment on logout-all/password change; verifySession compares. | Logout and password change take effect immediately. | P2 | S | 04 Security
S-04 | Security | Rate limiting only in the app | The DB-backed limiter works but runs after the request reaches the function. | Add edge/WAF rate limits for /api/auth/*. | Netlify rate-limit rules or a CDN WAF in front of the site. | Brute-force traffic stopped before it costs compute. | P3 | S | 04 Security
U-01 | User experience | No navigation on mobile | The sidebar is hidden below the md breakpoint and the mobile header only has 'BSA' and Logout — a broker on a phone can't reach Intake, Screening or Reports. | Add a mobile menu (drawer) using the same SidebarNav items. | components/MobileNav.tsx (button + slide-over), rendered in app/(app)/layout.tsx header; test at 375 px. | Field brokers can use BSA fully on a phone. | P1 | S | 01 Senior Web · 07 Broker
U-02 | User experience | Proxy corridor can't be corrected by the user | When no corridor matches, the Lease tab says it's a proxy but offers no way to pick the right corridor. | Add a corridor picker on the Lease tab (list from lease_comp corridors for the site's region). | GET /api/lease-benchmark/corridors?region=; select on LeaseTab; re-benchmark via existing POST. | Brokers fix the benchmark themselves instead of getting a proxy. | P2 | S | 01 Senior Web · 03 API | R-01
U-03 | User experience | Territory map ring colour can lag the verdict | Noted in QA: the map ring uses the map component's own verdict and can show green while the stats say 'Redistributes'. | Pass the blended verdict into TerritoryMap. | One prop change in SiteIntelligenceTabs → TerritoryMap. | Map and verdict always agree. | P2 | S | 01 Senior Web
U-04 | User experience | Stale AI write-up after saving an asking rent | Saving a rent updates the score, but the cached write-up still describes the old lease read (the user is told to regenerate). | Mark the analysis stale when module results change and offer a one-click refresh (not counted against the regenerate cap). | On lease save / re-run, set analysis payload.stale = true; Analysis tab shows a 'Figures changed — refresh' banner; generation with reason 'stale' bypasses the cap. | The write-up never contradicts the numbers on screen. | P2 | S | 10 AI Systems · 01 Senior Web

## Cavite-Batangas Data Plan
Expanding BSA to Cavite & Batangas — getting the data (Overpass API + official sources) into Neon Postgres
OpenStreetMap via the Overpass API gives establishments, malls, transport and (partly) barangay boundaries/populations. Population, zonal values, lease comps and traffic come from official or broker sources. Every step writes to the existing Neon tables through idempotent loaders, keeps its Truth Layer, and is re-runnable. Overpass is a shared free service: stay under ~10,000 queries and ~1 GB per day, run sequentially with pauses, and credit OpenStreetMap (ODbL).
Step | Phase | What | Source / API | How (method) | Implementation needed | Neon table(s) written | Truth Layer | Done when (desired outcome)
1 | 0 · Prepare | Region registry + schema columns | — | Define Cavite and Batangas once: PSGC province codes, bounding boxes, Overpass area names, warm-grid centres, corridor names. | lib/geo/regions.ts (see Backlog R-01). Migration: add region, province, psgc_code to poi, candidate_site, mall_property; add admin_boundary table (R-02). CLI flag --region=cavite¦batangas on ingest scripts. | (schema only) | — | npx prisma migrate deploy applies cleanly on Neon; npm run typecheck passes.
2 | 1 · Boundaries | Barangay / city / province polygons | PSGC shapefiles (altcoder/philippines-psgc-shapefiles, PSGC Q4-2023, MIT). Cross-check: OSM boundary=administrative, admin_level=4 (province) / 10 (barangay). | Download PH_Adm2/Adm3/Adm4 shapefiles; filter to Cavite and Batangas by PSGC province code; convert to GeoJSON (ogr2ogr) and load. Use OSM relations only to fill gaps. | prisma/loadBoundaries.ts --region=… : read GeoJSON → INSERT … ON CONFLICT (psgc_code) with ST_GeomFromGeoJSON → GiST index. Verify counts vs PSA barangay lists. | admin_boundary | Verified (official PSGC) | Every Cavite/Batangas barangay has a polygon; ST_Contains returns one barangay for any point in the province.
3 | 2 · Establishments (Overpass) | Competitor POIs for all 20 verticals | Overpass API (overpass-api.de + 2 mirrors already configured) | Query per province area (area["admin_level"="4"]["name"=…]) or per tile inside the province bbox; one vertical per query; out center; adaptive split when a tile hits the result cap. 2.5 s pause between calls; resume from poi_coverage checkpoints. | Extend prisma/ingestOsm.ts: --region, tile loop (R-03), write via loadPoi (upsert on osm_id), stamp poi_coverage(source='bulk'). Then SQL snap: UPDATE poi SET barangay/city/province/psgc_code FROM admin_boundary WHERE ST_Contains(geom, poi.geom). | poi, poi_coverage | Verified (coordinates) · category mapping Assumed | Per-vertical counts logged per tile; no tile at the cap; POIs carry barangay + city.
4 | 2 · Establishments (Overpass) | Brand branches (≈70 chains) | Overpass API — brand / name / brand:wikidata tags | Run the existing BRAND_PULL list against each province area. | ingestOsm.ts --region=… --brands (existing brandBranchesInBbox, bbox → region). | poi | Verified (coordinates) | Known chains (Jollibee, Mercury Drug, 7-Eleven, Puregold…) mapped in both provinces.
5 | 2 · Establishments (Overpass) | Transport + anchors for access/traffic proxies | Overpass: public_transport, railway=station, amenity=bus_station, office=*, shop=mall | One sweep per category per province (lower density → fewer tiles). | osmService selectors for transport/office/mall already exist → categories 'transport', 'office', 'mall'. Feeds D-01 accessibility pillar and the Land traffic fallback. | poi | Verified | Transport and office anchors present; Land module no longer 'unknown traffic' in town centres.
6 | 3 · Malls | Mall list with tier + footfall | Overpass shop=mall (names + coordinates) + broker review | Pull malls, export a review sheet, broker assigns tier (A/B/C) and footfall band, then load. | scripts/exportMalls.ts --region=… → CSV → reviewed → prisma/data/malls.<region>.json → loadMalls (upsert on name + city). | mall_property | Coordinates Verified · tier/footfall Assumed | Mall module scores Cavite/Batangas sites within 3 km of a mall.
7 | 4 · Demographics | Barangay population (and estimated bands) | PSA 2020 Census of Population & Housing (Region IV-A barangay tables). Cross-check: OSM place nodes with population=* and ref (PSGC). | Match PSA rows to admin_boundary by PSGC code; add income band (PSA FIES/regional proxies) and daytime population estimates as Assumed. | ETL → prisma/data/demographics.<region>.json (psgc_code, barangay, city, population, income_band, daytime_pop, truth_layer per field) → loadDemographics with geom from admin_boundary (replaces the 600 m circle). | demographic_cell | Population Verified · bands Assumed | Site Fit, Daypart and White-Space score provincial sites; confidence no longer forced Low.
8 | 5 · Zonal values | BIR zonal values | BIR zonal schedules — RDO 54A (Trece Martires, East Cavite), RDO 54B (Bacoor, West Cavite), RDO 58 & 59 (Batangas) | Download the latest schedules; run the NCR zonal ETL (label canonicalisation, ₱ parsing, barangay + city grain). | Generalise the zonal ETL (--region); canonicalCity for provincial LGUs; loadZonal (natural key region+city+barangay+rdo+class). | zonal_value | Verified (BIR) — tax-reference floor only | Zonal band + cross-check shown for provincial sites; zoning screen not 'unknown'.
9 | 6 · Lease comps | Corridor rent comparables | Grid broker network · public listings (verify) · signed leases | Collect ≥5 comps per corridor × format; record observed_date and source. | Capture template → prisma/data/lease.<region>.json → loadLease; add corridors to the region registry + inferCorridor(region). | lease_comp | Verified only for confirmed leases · else Assumed | Lease Benchmark uses local corridors; proxy flag gone for covered corridors.
10 | 7 · Traffic | Arterial traffic bands | DPWH AADT counts; seasonal multipliers per existing model | Add the main provincial arterials as corridors with AADT-anchored bands. | Append rows to prisma/data/trafficSeasonality.real.json → npm run db:seed-traffic. | traffic_corridor | Assumed (AADT-anchored) | Land & Traffic uses corridor bands for key roads.
11 | 8 · Wire up | Resolvers, warm grid, UI | — | Make runtime lookups region-aware and pre-warm the on-demand cache for busy provincial centres. | inferCorridor/canonicalCity by region; region warm centres (e.g. Imus, Dasmariñas, Bacoor, General Trias, Tagaytay, Batangas City, Lipa, Sto. Tomas); /api/admin/warm accepts area:'cavite'¦'batangas'. | poi_coverage | — | A new Cavite/Batangas site loads without cold-cache delays.
12 | 9 · Validate | Data checks + journey QA | — | Run validators and scripted journeys; compare counts to known totals. | npm run db:validate (extend with per-region checks: barangays with population, POIs per 10k people, comps per corridor); qa_calabarzon.ts (Backlog R-08). | — | — | Validation report clean; QA scenarios pass; results logged in WORKLOG.

## Overpass Query Templates
Overpass QL templates (to be wrapped by lib/places/osmService.ts)
Test any query at overpass-turbo.eu first. Keep [timeout:90]; one vertical per query; sequential runs with ~2.5 s pauses (already the ingest default). Replace {BBOX} with south,west,north,east of a tile.
Purpose | Overpass QL | Notes | Maps to
Province area handle (Cavite) | [out:json][timeout:90]; area["boundary"="administrative"]["admin_level"="4"]["name"="Cavite"]->.prov; nwr["amenity"~"^(fast_food¦restaurant¦cafe)$"](area.prov); out center 2000; | Province = admin_level 4 in OSM Philippines. Use name="Batangas" for Batangas. Area queries are simplest but can time out for dense categories — prefer tiles for food/retail. | poi (competitor)
Tiled sweep (preferred for dense verticals) | [out:json][timeout:90]; ( nwr["amenity"="pharmacy"]({BBOX}); nwr["healthcare"="pharmacy"]({BBOX}); ); out center 600; | Tile ~0.05°–0.1°. If the result count equals the limit, split the tile into 4 and re-query. Clip results to the province polygon in SQL afterwards. | poi (competitor)
Brand branches | [out:json][timeout:90]; area["admin_level"="4"]["name"="Batangas"]->.prov; nwr["brand"~"Jollibee",i](area.prov); nwr["name"~"Jollibee",i](area.prov); out center 300; | Same pattern as the existing BRAND_PULL; add brand:wikidata where known for precision. | poi (competitor)
Malls | [out:json][timeout:90]; area["admin_level"="4"]["name"="Cavite"]->.prov; nwr["shop"="mall"](area.prov); out center; | Export for broker tier/footfall review before loading. | mall_property
Transport anchors | [out:json][timeout:90]; area["admin_level"="4"]["name"="Cavite"]->.prov; ( nwr["public_transport"="station"](area.prov); nwr["amenity"="bus_station"](area.prov); nwr["railway"="station"](area.prov); ); out center; | Feeds the Site Fit accessibility pillar (Backlog D-01) and the Land traffic fallback. | poi (transport)
Barangay boundaries (cross-check) | [out:json][timeout:180]; area["admin_level"="4"]["name"="Batangas"]->.prov; rel["boundary"="administrative"]["admin_level"="10"](area.prov); out geom; | Barangay = admin_level 10 (admin_type:PH=barangay). OSM coverage is uneven outside Metro Manila — use PSGC shapefiles as the primary source. | admin_boundary (gap-fill)
Barangay place nodes with population (cross-check) | [out:json][timeout:90]; area["admin_level"="4"]["name"="Cavite"]->.prov; node["place"]["population"](area.prov); out; | PH mapping convention adds population + PSGC ref to barangay place nodes where mapped. Use only to sanity-check PSA figures. | demographic_cell (QA only)

## Data Coverage Matrix
Reference data coverage by area (today) and where the missing data comes from
Dataset | Neon table | NCR | Davao | Cavite | Batangas | Source to fill gaps | Truth Layer when loaded
Establishments / competitors | poi | Bulk NCR sweep + on-demand cache (capped per query) | Partial (populate --region=davao) | On-demand cache only (per report, ~1 km cells) | On-demand cache only | Overpass tiled sweep (Plan steps 3–5) | Verified coordinates
Administrative boundaries | (new) admin_boundary | None — 600 m circles | None | None | None | PSGC shapefiles; OSM admin_level 4/10 cross-check | Verified
Demographics | demographic_cell | 283 barangays (Assumed) | 13 cells | None | None | PSA 2020 CPH barangay tables | Population Verified · bands Assumed
BIR zonal values | zonal_value | 2,317 rows (San Juan + Valenzuela bgy missing) | None | None | None | BIR RDO 54A / 54B | BIR RDO 58 / 59
Lease comparables | lease_comp | ~15 corridors, 80 comps (NCR + Davao) | Included in the 15 | None (Bacoor → Las Piñas proxy; else QC proxy) | None (QC proxy) | Broker network + confirmed leases | Verified if confirmed · else Assumed
Malls | mall_property | 33 NCR malls | None | None | None | Overpass shop=mall + broker tiering | Coords Verified · tier Assumed
Traffic corridors | traffic_corridor | NCR corridors (of 15) | Davao corridors (of 15) | None | None | DPWH AADT | Assumed
Competitor sets | competitor_set | National (89 anchors) | National | National | National | — | As loaded
Franchise requirements | franchisor.requirements | National (161 brands) | National | National | National | — | As loaded
Note: 'None' means sites there fall back to proxies (flagged Projected in the app) or leave the module unscored.

## Sources
Sources
Topic | Reference | Used for
Overpass usage guidance | https://dev.overpass-api.de/overpass-doc/en/preface/commons.html | ~10,000 requests/day and ~1 GB/day guideline; run own instance if more is needed
OSM PH barangay tagging | https://wiki.openstreetmap.org/wiki/Tag:admin_type:PH=barangay | Barangay = admin_level 10; optional population and PSGC ref tags
OSM PH mapping conventions | https://wiki.openstreetmap.org/wiki/Philippines/Mapping_conventions | Province = admin_level 4 boundaries
PSGC boundary shapefiles | https://github.com/altcoder/philippines-psgc-shapefiles | Region/province/city/barangay polygons (PSGC Q4-2023, MIT licence)
PSA 2020 CPH — CALABARZON | https://psa.gov.ph/content/highlights-region-iv-calabarzon-population-2020-census-population-and-housing-2020-cph | Cavite 4,344,829 and Batangas 2,908,494 (2020); barangay tables for demographics
BIR zonal values | https://www.bir.gov.ph/zonal-values | Schedules for RDO 54A, 54B (Cavite) and 58, 59 (Batangas)
RDO 54 split (54A / 54B) | https://www.scribd.com/document/412950747/RDO-No-54B-Bacoor-City-West-Cavite | Which Cavite LGUs fall under each RDO (verify against the BIR page)
OpenStreetMap licence | https://www.openstreetmap.org/copyright | ODbL attribution required wherever OSM-derived data is shown
Internal | 4 - Final Application: WORKLOG.md, PROJECT_MEMORY.md, docs/HANDOFF.md, docs/SECURITY_POSTURE.md | Open items from the 23 Sep 2026 review and fix batches 1–5